ANNEX II: TERMS OF REFERENCE

1.	BACKGROUND INFORMATION	2

1.1.	Partner country	2

1.2.	Contracting Authority	2

1.3.	Country background	2

1.4.	Current situation in the sector	2

1.5.	Related programmes and other donor activities	2

2.	OBJECTIVE, PURPOSE & EXPECTED RESULTS	2

2.1.	Overall objective	2

2.2.	Purpose	3

2.3.	Results to be achieved by the Contractor	3

3.	ASSUMPTIONS & RISKS	3

3.1.	Assumptions underlying the project	4

3.2.	Risks	4

4.	SCOPE OF THE WORK	4

4.1.	General	4

4.2.	Specific work	5

4.3.	Project management	7

5.	LOGISTICS AND TIMING	7

5.1.	Location	7

5.2.	Start date & Period of implementation of tasks	7

6.	REQUIREMENTS	8

6.1.	Staff	8

6.2.	Office accommodation	8

6.3.	Facilities to be provided by the Contractor	8

6.4.	Equipment	Error! Bookmark not defined.

7.	REPORTS	8

7.1.	Reporting requirements	8

7.2.	Submission and approval of reports	8

8.	MONITORING AND EVALUATION	9

8.1.	Definition of indicators	9

8.2.	Special requirements	9

# BACKGROUND INFORMATION

## Partner country

Republic of Serbia

## Contracting authority

Citizens' Association "Institute for Progress and Collaboration of the  Western Balkans Regions"

## Country background

Tourism has lots of potentials to be one of the key economic development branches connecting people in Bulgaria and Serbia, with lots of underdeveloped sectors and areas. Still general condition of one of the greatest touristic attractions in the region, the great Nisava Fortress from medieval age, as one of the Serbian monuments of great importance, and the Sofia Ancient Mausoleum are being devastated, ruined and underutilised for the long period of time. Thus, there are possibilities for development and full exportation of those two sites, according to the domestic legislation. By developing joint investments in the touristic infrastructure will increase competitiveness of the region and the strengthening tourist market, introducing Sofia and Nis and leaders of joint CBC tourist measures and will enhance economic development of the Sofia and Nis and encourage promotion and raising awareness of local touristic products, that most of the people are not aware of. Needs: A new touristic infrastructure, supported with new touristic services should be built up or renewed. It will support employment, economic growth and decrease strong socio economic pressure in the region. A need for new project management knowledge is essential in order to validate all touristic, cultural and general strengths and potentials in the region. Strengths: Rich cultural heritage in cross border region. Tourists have awareness of historical sites in Sofia and Nis and visit them as touristic destinations of great importance and high attractiveness. Constraints: lack of communication and cooperation between different institutions and bodies in charge for taking care and utilisation of those monument sites. Proposed strategy: Gathering all key players and stakeholders on improving the poor condition of those two locations, and their development and opening to the wider population and awareness raising of their importance and their touristic significance.

Current situation in the sector

The project invests in the effective valorisation and the efficient management of the cultural and historical heritage assets of the territory (Nis Fortress and Sofia Ancient Mausoleum), promotes the balanced development of history tourism thus valorising the favourable conditions for diversified tourism in the border area, leading to smart economic growth of the Bulgaria-Serbia border region area. It exploits different form of practice for revitalisation and utilisation of heritage sites, disseminate these best practices and delivering common utilization strategy thus promoting joint territorial management by the regional authorities and balancing the conserving and developing aspects of natural resources in creating sustainable tourist attractions used to improve the quality of visiting environment and also to contribute to the quality of living environment. These territorial development approaches are designed to be fully in line with the overall aim of the programme

## Related programmes and other donor activities

Not applicable

# OBJECTIVE, PURPOSE & EXPECTED RESULTS

## Overall objective

The overall objectives of the project are as follows:

- Increasing the touristic attractiveness of Sofia and Nis.

## Purpose

The purposes of this contract are the following services to be provided, which are needed for implementation of project activities:

Development of 3D model of Niš Fortress

## Results to be achieved by the contractor

- 3D model of Niš Fortress  created for the purpose of visualization, conservation and tourists advertising.

# ASSUMPTIONS & RISKS

## Assumptions underlying the project

Implementation of the project will be supported with the successful implementation of this contract.The following assumptions can be made in order to reduce the risks related to delay or non-realization of the activities, subject to this Terms of Reference:

- Clear understanding of the contract purpose and tasks on behalf of the Contractor;

- Full cooperation between the Contracting Authority and the Contractor in view to fulfil the tasks on time, with high quality and within the budget limitation;

- Timely information for the respective place and date of the events provided by the Contracting Authority.

## Risks

There are no greater risks during the implementation of the project. The Contracting Authority should provide to the Contractor the necessary information for the fulfillment of the tasks.

# SCOPE OF THE WORK

## General

### Description of the assignment

Promoting of the Nis Fortress is obligatory part of the project. The best way this to be done is with help of modern and state of the art technologies. In order the Mausoleum to be presented in the best way a 3D model will be created for the purpose of visualization, conservation and tourists advertising

### Geographical area to be covered

The contract will be realized in the territory of City of Niš

### Target groups

Youth and inhabitants of Serbia and youth around the world, touristic organizations, beneficiaries of the project, research institutions, government and non-governmental organizations.

## Specific work

"Promoting of the Nis Fortress is obligatory part of the project. The best way this to be done is with help of modern and state of the art technologies. In order the Mausoleum to be presented in the best way a 3D model will be created for the purpose of visualization, conservation and tourists advertising.

Our aim is to achieve development the Virtual Reality (VR) web portal, including software tool based on the three dimensional (3D) model of Nish fortress. This portal should represent a modern way to popularize the most representative object of the city, and also the one of the most important cultural heritage artefact in this part of Europe. Using developed VR portal according to the created 3D mesh, all accompanying web content should be developed also. Some of the representative rendered images and videos should be posted on Facebook page and YouTube channel of organizations possessing the mentioned social media for project promotion.

Task aims to form a team of experts in different areas to realize this nontrivial idea. The main goal is developing a tool for an automatic 3D models creation. This kind of algorithms require understanding and application of novel results of resent research in the field of Structure from Motion photogrammetric range imaging techniques. Justification of the use of such technologies lies in a proven better perceptual experience of observers. The secondary effect would be spread visual information to world web users. The VR portal as a complex web structure should be developed by the specialized team experts separately in four phases: i) recording video of the terrain and the fortress ambient, archiving and digitizing; ii) texture mapping and creating 3D models; iii) The Virtual 3D software tool development and its implementation into the VR web portal structure; iv) development and application of accompanying web content.

# Preparing data for extraction

The first step of the project realization should provide all material for further software development. In order to achieve enough accuracy of terrain detail, this step firstly should include video recording in High Quality (HQ) resolution.

Recorded set of huge resolution images and 4K HQ video should be composited and edited in accordance to real fortress structure, and thus prepared for the next 3D reconstruction step.

All Two Dimensional (2D) materials, including previously recorded video, but also scanned old photos and flowchart drawings, should be resized and converted to feature determination and texture mapping.

The data should be subsequently sorted, archived and adapted to the speed data management system that should be realized through data matrix and vectors.

# Automatic 3D model creating

In the next phase, SfM algorithm should be developed and optimized for the project purpose. The main issue of this task is increasing a computation speed of big data set. This issue should be overcome by creating a new optimized algorithm for fast simulation.

3D models should be extracted using previously developed algorithm for automatic 3D mesh construction and prepared video and image set. Under the project condition, this massive 3D

structures would contain huge number of primitives (vertices and faces) and should be refined and optimized for the web use.

The same prepared material set should be used again for texture creation and mapping. Due to wide recorded area and huge number of pixels, textures should be optimized for several resolution requirements and zooming levels.

Result of this step should be 3D structures of the fortress that are constructed directly from video motion and image set. Obtained mesh with belonging texture and pattern maps should be prepared for VR and web use.

# VR web portal developing

This development process consists of two sub-processes: i) Virtual 3D tool creation and ii) Web portal development. The first one should use previously constructed 3D model to form desired virtual environment. Motion trough the VR environment should be smooth and performed in real time.

Web development of portal should be combination of the standard web-user requirements and solving the unique VR issues. Firstly, navigation and desktop structure should be user-friendly and intuitive for a wide spectrum of users.

Web portal should contain supported images that are developed during the project. All images will be delivered by Contracting Authority and the Project Team. Portal would be accessible to multiple platforms including smartphones, computers, tablets, laptops and other electronic devices.

# Applications and advertisement

Advertisement of the product will be sole responsibility of the Project Partners and will be conducted via social media and internet presentations. Also on all the promotional events Project Partners will promote the activity and present its results.

# Outputs of the activity:

Output of the activity will be developed 3D model of Mausoleum in Niš with accurate Historical data available to the visitors of the Mausoleum and available on the websites of the Beneficiaries. This activity will be promoted also in the media that will be engaged during the project implementation. Not only visitors but entire region will be available to see 3D model online and visit it in Future.

## Project management

### Responsible body

Citizens' Association "Institute for Progress and Collaboration of the  Western Balkans Regions"

### Management structure

The responsible persons for implementation of the tasks related to this project and this contract, in the Contracting Authority is Bratislav Stoiljković-Project Coordinator.

### Facilities to be provided by the contracting authority and/or other parties

For this tender, there is no need to provide more facilities. The Contracting Authority will timely provide necessary information such as: the specific time and place of events, agendas and similar.

# LOGISTICS AND TIMING

## Location

The project activities related to this Contract will be realized in City of Niš, Republic of Serbia

## Start date &period of implementation of tasks

The intended start date is 25.05.2020 and the period of implementation of the contract will be 6 months from this date. Please see Articles 19.1 and 19.2 of the special conditions for the actual start date and period of implementation.

# REQUIREMENTS

## Staff

Note that civil servants and other staff of the public administration of the partner country, or of international/regional organisations based in the country, shall only be approved to work as experts if well justified. The justification should be submitted with the tender and shall include information on the added value the expert will bring as well as proof that the expert is seconded or on personal leave.

### Key experts

Key experts are not required.

### Other experts, support staff & backstopping

The contractor has to ensure sufficient number of qualified experts for quality and timely implementation of tasks planned by these Terms of References. These experts are considered as non-key experts therefore their CVs will not be submitted with the application.

## Office accommodation

Office accommodation for each expert working on the contract is to be provided by Contractor and will be included in the global price.

## Facilities to be provided by the contractor

## N/A

## Equipment

N/a.

# REPORTS

## Reporting requirements

The contractor will submit the following reports in English in one original and one copy:

- First Interim Report shall be submitted at the end of Month 1 of Contract realization.

- Second Interim Report shall be submitted at the end of Month 3 of Contract realization

- Final report prepared in English language shall be submitted no later than 5 (five) working days after the end of implementation of tasks under the current Contract. It should provide conclusions and clear evidence of the implementation of all requested services. Approval of the final report by the Contracting Authority will be a basis for final payment under the contract. The final report must be provided along with the corresponding invoice.

## Submission and approval of reports

The report referred to above must be submitted to the Project Coordinator identified in the contract. The Project Coordinator is responsible for approving the reports.

# MONITORING AND EVALUATION

## Definition of indicators

The indicator of the successful implementation of the contract is all services provided in time, quality and quantity manner as required in these Terms of Reference.

## Special requirements

Not applicable